## 7-Day Plan
STT v2 + Emotion — Compressed 7-Day Delivery Plan (1 Developer)
Data: 2 podcasts (2+2 hrs) + ~1 hr fresh recordings ¦ Start: Tue, 14-Jul-2026 ¦ End: Wed, 22-Jul-2026
Day | Date | Task | Output | Track
Day 1 | 14-Jul (Tue) | Denoise & normalize audio; segment into 15-30s clips; speaker diarization | Clean, segmented, speaker-tagged audio | Shared
|  | Kick off automated draft transcription (Whisper base) — runs in background overnight | Draft transcripts generating | Shared
Day 2 | 15-Jul (Wed) | Manual transcript correction & verification | Verified, low-WER transcripts | STT
|  | Accent tagging (Karachi/Lahori/Punjabi-influenced, etc.) | Accent-labeled dataset | STT
|  | Emotion labeling (neutral/happy/angry/sad) per segment | Emotion-labeled dataset | Emotion
|  | Train/val/test split — both datasets (80/10/10) | Split datasets ready | Shared
Day 3 | 16-Jul (Thu) | Base model selection (Whisper large-v3 or stack-compatible) | Model config | STT
|  | LoRA/PEFT fine-tuning setup | Training pipeline | STT
|  | Kick off STT training run — background, continues overnight | Training in progress | STT
Day 4 | 17-Jul (Fri) | Monitor & complete STT training run | Fine-tuned STT model | STT
|  | Emotion classifier architecture choice (head on wav2vec2/HuBERT embeddings) | Model config | Emotion
|  | Emotion training pipeline setup; kick off training run — background overnight | Training in progress | Emotion
Day 5 | 20-Jul (Mon) | Monitor & complete Emotion training run | Emotion classification model | Emotion
|  | STT WER/CER evaluation: v1 vs v2 | Comparison report | STT
|  | STT accent-wise performance breakdown | Accent performance report | STT
Day 6 | 21-Jul (Tue) | Emotion accuracy/F1 per class | Confusion matrix + metrics report | Emotion
|  | CTranslate2/ONNX export (STT) | Deployable STT model | STT
|  | Emotion model export/serving setup | Deployable emotion model | Emotion
Day 7 | 22-Jul (Wed) | End-to-end integration test — both models in pipeline | Verified integrated pipeline | Shared
|  | Buffer: bug-fix, edge cases, sign-off | Final delivery | Shared
TOTAL: 7 working days |  | Tue 14-Jul-2026 → Wed 22-Jul-2026 (Mon-Fri only, 1 developer)
Note: This is a compressed timeline vs. the original ~14.5-day estimate. It works by (1) treating GPU training as background/overnight, not blocking dev time, (2) folding accent tagging into the transcript QA pass, and (3) trimming evaluation depth to what's needed for a v1/baseline sign-off. Given only ~5 hrs of audio split across accent + 4 emotion classes, treat the emotion model as a first-pass baseline — expect a follow-on iteration once more labeled data is available. Any GPU slowdown, noisy data, or QA rework will push past Day 7.