## Banking Whisper Plan
Whisper Fine-Tuning Plan — Urdu Banking Call-Center / IVR (Auton8 / DeepPulse)
Target: production-grade Urdu STT for real-time call-center / IVR voice agent, on-prem / air-gapped deployable
Phase | Task | Effort | Output | Risk / Note
0. Compliance & Governance | Define PII handling policy: CNIC, account numbers, card numbers, amounts must be masked/redacted before data leaves controlled environment | 2-3 days | Data governance policy + redaction spec | Banking call data is regulated (SBP) — this is a hard prerequisite, not optional, even for air-gapped training
| Set up air-gapped data pipeline (no data egress) matching existing BAFL/Alex Bank deployment pattern | 1-2 days | Isolated training environment | Reuse existing air-gapped infra pattern from CADPilot/DeepPulse deployments
1. Data Collection | Source historical call recordings (agent + customer channels) from IVR/call-center system | TBD — depends on client access | Raw call corpus | Volume unknown — flag: need target hour count from client before locking timeline
| Assess coverage: dialects/accents, call types (balance inquiry, complaint, transfer, Islamic banking queries) | 1 day | Coverage gap report | Uneven call-type coverage will show up as blind spots later
2. Data Prep | Redact/mask PII in audio + transcripts (CNIC, account #, card #, amounts) | 3-5 days | PII-safe dataset | Automate this — manual redaction won't scale past a few hours
| Resample/normalize telephony audio (8kHz → 16kHz), denoise, handle codec artifacts (G.711/G.729) | 1-2 days | Model-ready audio | Telephony audio is a real domain mismatch vs Whisper's clean 16kHz training data
| Speaker diarization: separate agent vs customer channel | 1 day | Channel-separated segments
| Domain augmentation: add telephony-style noise/codec compression to existing clean 5hr podcast set to bridge domain gap | 1-2 days | Augmented training set | Bootstrap strategy if call-recording volume is initially thin
3. Annotation & QA | Transcribe with code-switch handling (Urdu-English mixed, e.g. 'mera account block ho gaya hai') | domain-heavy, scales with hours | Verified transcripts | Code-switching is the single biggest failure mode for generic Urdu ASR in banking calls
| Build banking-domain glossary (T24 terms, Islamic banking terms, product names) for annotator consistency + model vocabulary boost | 2 days | Domain glossary + normalized number/amount format
| Train/val/test split, stratified by call type and channel | included | Split dataset
4. Fine-tuning | Base model selection (Whisper large-v3, faster-whisper/CTranslate2-compatible) | 0.5 day | Model config | Must be CTranslate2-exportable for the existing faster-whisper serving stack
| LoRA/PEFT fine-tune with telephony + code-switch augmented data | 3-5 days | Fine-tuned checkpoint | Duration scales with data volume — see Phase 1 flag
| Domain vocabulary/prompt biasing for account numbers, amounts, banking terms | 1-2 days | Biased decoding config
5. Evaluation | WER/CER vs generic Whisper baseline, on held-out real call data | 1 day | Comparison report
| Targeted accuracy: account/CNIC number recognition, code-switch segments, per call-type | 1-2 days | Domain accuracy report | Generic WER can look fine while numeric recognition — the part that actually matters for IVR — is still weak
| Latency benchmark under real-time streaming constraints | 1 day | Latency report | IVR needs sub-second response — batch-mode WER numbers don't guarantee this
6. Deployment & Integration | Export via CTranslate2 for faster-whisper serving | 0.5 day | Deployable model
| Integrate into Auton8/DeepPulse voice pipeline (Kamailio/FreeSWITCH streaming, VAD chunking) | 2-3 days | Integrated STT service | Streaming/chunked inference is architecturally different from the batch fine-tuning/eval above
| End-to-end test on live-call simulation | 1 day | Verified pipeline
7. Production Monitoring | Set up misrecognition feedback loop (flagged calls → next training batch) | 1-2 days | Continuous improvement loop | Without this, model quality stalls at v1 — call center language drifts (new products, new complaint patterns)
Key assumption: exact hours of banking call data available is unknown, so Phases 1, 3, and 4 are not day-costed the way the earlier podcast plan was — actual timeline depends heavily on that number. As a rule of thumb, telephony + code-switch domain adaptation typically wants materially more than 5 hours to generalize well; if initial call data is thin, the augmentation step in Phase 2 (adding telephony noise/codec artifacts to the existing clean podcast set) is the fastest way to get a usable v1 while more real call data accumulates.